## Slide 1
Alberta data centres
Capital exposure and decisions for Infrastructure
September 2026
Notes: Independent analysis. Colour reference: https://www.alberta.ca/colour-palette. Government of Alberta blue, sky and prairie palette. No government endorsement implied. Project snapshot 31 August 2026. Source dates are retained on each evidence slide.

## Slide 2
A proposed pipeline meets an active construction market
19 identified data-centre records sit alongside substantial infrastructure investment.
Sources: Alberta Major Projects, 31 Aug 2026; Alberta first-quarter fiscal update, 2026–27
2
Chart: 
| Proposed | Under construction
Data-centre records | 15 | 4
$10.687B
Updated Alberta capital plan for FY2026–27
Shared trades and suppliers create potential competition as projects advance.
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
https://open.alberta.ca/dataset/9c81a5a7-cdf1-49ad-a923-d1ecb42944e4/resource/eaeb7a75-0c9f-4964-be53-0f1cc889ffab/download/tbf-2026-27-first-quarter-fiscal-update-economic-statement.pdf
The 19 core records can represent phases or multi-location programmes, rather than unique campuses. Three enabling power records are separate. Proposed status does not establish financing, procurement or construction start. The capital plan spans different asset classes and includes more than construction labour.

## Slide 3
Seven reported projects account for $49.01B
Reported investment estimates, CAD billions.
Source: Alberta Major Projects, 31 Aug 2026. Twelve additional core records have no reported cost.
3
Chart: CAD billions
| Malachite One | Meta | Wonder Valley P1 | Beacon Foothills | Crusoe Alberta | TNE Data District P1 | eStruxture CAL-3
Reported CAD billions | 15 | 13 | 12 | 4 | 3 | 1.26 | 0.75
Construction-only scope is bracketed in the labour sizing scenario.
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Seven core estimated costs sum to CAD49.01B. The other 12 core records lack costs. The sum excludes CAD6.40B from three enabling power records. Amounts may include servers, land and enabling works. No uniform construction or labour share is applied. Names are shortened on the chart; the appendix carries the full record names.

## Slide 4
Demand concentrates in shared construction packages
Civil works establish the site. Electrical and cooling systems drive specialist fit-out.
Engineering scope classification; actual crew and supplier overlap depends on package timing and location.
4
Package | Labour demand | Materials and equipment
Civil / structural | Operators, labourers, formwork crews, finishers, ironworkers | Concrete, aggregate, reinforcing and structural steel
Electrical | Electricians, cable installers, controls and testing specialists | Transformers, switchgear, cable, UPS and generators
Mechanical / cooling | HVAC and sheet-metal workers, pipefitters, plumbers, insulators | Chillers, air handlers, pumps, pipework and ducts
Utility connections | Line crews, utility engineers and enabling civil crews | Substations, connection equipment and utility corridors
Notes: Engineering interpretation of typical data-centre construction packages. The table identifies shared resources, not measured project quantities or incremental Alberta job demand. Site location, cooling design, electrical architecture and prefabrication determine the final scope. Electrical utility connections and permitting can be separate from the building contract.

## Slide 5
The stress range is hundreds to low thousands of trade FTE
Illustrative five-year allocation of the costed pipeline. Low/high assumptions remain visible.
Analyst stress cases. Gross average workload, not a labour shortage or delivery forecast.
5
Input / result | Low case | High case
Pipeline realization | 25% | 75%
Construction / labour shares | 30% / 30% | 50% / 40%
Paid labour cost / hour | $100 | $80
Construction volume | $3.7B | $18.4B
Electricians: annual average FTE | 240 | 1,998
HVAC mechanics: annual average FTE | 120 | 999
Both: 5 years; 1,840 paid hours/FTE-year; electrician/HVAC payroll shares 20% / 10%.
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Statistics Canada, Alberta observations. Census Table 98-10-0449-01, May 2021 employed persons: https://www150.statcan.gc.ca/t1/tbl1/en/tv.action?pid=9810044901
Job Vacancy and Wage Survey, Table 14-10-0444-01, Q1 2026: https://www150.statcan.gc.ca/t1/tbl1/en/tv.action?pid=1410044401
Analyst-selected bracket, not empirically calibrated probabilities, rates or cost shares. Construction = reported costed capex × realization × construction share. Paid labour hours = construction × labour share / fully loaded paid-hour cost. Trade FTE = paid hours × trade payroll share / 1840 / 5. No licensed productivity rates implied. Treating scope-diverse reported investment with one construction share is an explicit stress assumption. The five-year allocation may be illustrated as 2026–2030, but is not supported by the six published completion dates and includes work that may already be underway. It is not a forward-only forecast. Peak quarterly activity and net Alberta hiring are not estimated. Three-year concentration multiplies annual averages by 5/3. High and low cases jointly vary assumptions, not statistical confidence bounds.

## Slide 6
The workforce comparison shows scale, not spare capacity
Scenario workload relative to historical Alberta employment stocks.
2021 Census stock denominator. Current availability requires contractor and regional evidence.
6
Occupation | 2021 employed | Low FTE / stock | High FTE / stock
Electricians, excluding industrial / power | 13,375 | 240 / 1.8% | 1,998 / 14.9%
HVAC mechanics | 3,095 | 120 / 3.9% | 999 / 32.3%
Timing matters: the same workload over three years raises annual averages by 67%.
Notes: Statistics Canada, Alberta observations. Census Table 98-10-0449-01, May 2021 employed persons: https://www150.statcan.gc.ca/t1/tbl1/en/tv.action?pid=9810044901
Job Vacancy and Wage Survey, Table 14-10-0444-01, Q1 2026: https://www150.statcan.gc.ca/t1/tbl1/en/tv.action?pid=1410044401
Numerator is conditional gross average FTE; denominator is historical employed persons across industries. These are scale comparisons, not current utilization, vacancy rates, shortages or employment growth. No assumption that the workforce is idle. HVAC mechanics do not represent the whole mechanical workforce. Workers may move across regions, projects or provinces. Published completion years do not establish a simultaneous peak.

## Slide 7
HVAC and steel prices show the largest increases
Calgary and Edmonton industrial-factory construction components, Q2 2026 versus Q2 2025.
Source: Statistics Canada, Table 18-10-0289-01. Contractor bid-price changes, not raw-material prices.
7
Chart: 
| Concrete | Structural steel | Electrical systems | HVAC
Calgary | 4.11 | 7.3 | 0.83 | 10.05
Edmonton | 5.24 | 10.44 | 1.01 | 10.05
HVAC and steel warrant a cost-weighted procurement review.
Notes: Statistics Canada, Building construction price indexes, Table 18-10-0289-01, Calgary and Edmonton industrial-factory components, Q2 2026 year-over-year changes. https://www150.statcan.gc.ca/t1/tbl1/en/tv.action?pid=1810028901
Year-over-year component changes from the industrial-factory archetype. It is a proxy for construction cost conditions, not a data-centre construction price index. Figures do not measure physical material volumes or supplier spare capacity, nor identify the causal contribution of data-centre activity.

## Slide 8
A 10% shock on a quarter of the plan is about $267M
Budget sensitivity against the $10.687B FY2026–27 capital plan.
Each row is a separate exposure test. Do not add them or layer them onto an escalated baseline.
8
Price movement | Calgary / Edmonton | Impact if 25% of plan exposed
Concrete | 4.11% / 5.24% | $110M / $140M
Structural steel | 7.30% / 10.44% | $195M / $279M
Electrical systems | 0.83% / 1.01% | $22M / $27M
HVAC | 10.05% / 10.05% | $269M / $268M
At a 10% shock: 10% exposed = $107M; 25% = $267M; 50% = $534M.
Notes: Statistics Canada, Building construction price indexes, Table 18-10-0289-01, Calgary and Edmonton industrial-factory components, Q2 2026 year-over-year changes. https://www150.statcan.gc.ca/t1/tbl1/en/tv.action?pid=1810028901
https://open.alberta.ca/dataset/9c81a5a7-cdf1-49ad-a923-d1ecb42944e4/resource/eaeb7a75-0c9f-4964-be53-0f1cc889ffab/download/tbf-2026-27-first-quarter-fiscal-update-economic-statement.pdf
Exposure share is an analyst assumption, not measured capital-plan composition. Impact = $10,687M × exposed share × observed YoY percentage/100. Each row assumes the same quarter of the plan independently exposed to that component movement. No rows are summed. The historical movement is applied as a stress, not a future forecast or AI-attributable premium. Use uncommitted scope, contract allocation of price risk and current baseline price date before reserving contingency. 1% of whole plan = $106.87M; 10% = $1,068.7M. The plan is consolidated provincial capital, not the Infrastructure ministry budget alone.

## Slide 9
49 Infrastructure-developer records overlap 2027–2036
Reported municipality and stage identify a portfolio for package-level review.
Developer is the screening field. Ownership, current package phase and actual shared crews require confirmation.
9
Project | Municipality | Reported stage / years
Alberta Surgical Initiative (02 - Calgary) | Calgary | Construction, 2024–2029
New K-9 Catholic School in Chestermere | Chestermere | Construction, 2025–2027
Red Deer Regional Hospital Centre Redevelopment | Red Deer | Construction, 2024–2031
Alberta Surgical Initiative (06 - Royal Alexandra Hospital) | Edmonton | Proposed, 2027–2028
Recovery Communities (10 - Grande Prairie) | Grande Prairie | Construction, 2026–2028
Package screen: electrical fit-out, cooling and commissioning. Full 49-record register follows.
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
Exact filter: developer equals Alberta Infrastructure and schedule_overlap_status equals overlaps in the canonical exposure CSV for 2027–2036. 245 Infrastructure-developer records in the source, 184 with incomplete schedules. This is not a legal title search or a complete list of all GoA-funded projects. Examples intentionally span Calgary/Chestermere, central Alberta, Edmonton and the northwest. Electrical, cooling and commissioning are engineering package intersections, not observed current phases. Beacon-area and Wonder Valley-area proximity does not establish a shared contractor. Missing schedules remain unknown. Full register preserves municipality, stage and reported year range.

## Slide 10
Power belongs in the delivery conversation
Three enabling-power proposals total $6.4B, separate from the core data-centre pipeline.
Sources: Alberta Major Projects, 31 Aug 2026; AESO large-load page checked 6 Sep 2026
10
Enabling-power proposal | Municipality | MW / reported end
Greenlight Electricity Centre | Sturgeon County | 932 MW / 2030
Teton Digital Black Bear Power Project | Swan Hills | 466 MW / 2028
Teton Digital Northern Forge Power Project | Greenview No. 16 | 200 MW / 2028
AESO Phase 1: 1,200 MW allocated to executed load contracts.
Infrastructure needs facility-level power-on milestones from AESO and local utilities.
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Greenlight Electricity Centre: https://greenlightelectricitycentre.ca/
Teton Digital Black Bear Power Project: https://www.tetondigital.io/black-bear
Teton Digital Northern Forge Power Project: https://www.tetondigital.io/northern-forge
https://www.aeso.ca/grid/connecting-to-the-grid/large-load-projects/
AESO checked 6 September 2026: Phase 1 allocates 970 MW to GLDC Load and 230 MW to Keephills Data Centre Phase I. The projects continue through the Connection Process. Phase 2A is a BYOG process. Executed contracts do not mean energized load. Generation proposals total 1,598 MW, distinct from load contracts and not a measure of spare network capacity. Their data-centre-enabling classification is analytical. No inference of a province-wide transmission shortage or a public-facility delay. Distribution service and equipment can matter independently of the large-load process.

## Slide 11
Equipment availability can govern delivery dates
Supplier lead-time benchmarks relevant to Alberta procurement planning.
SourceBlue, Q2 2026 US market ranges. Alberta delivery requires a product-specific supplier quotation.
11
Equipment | Published lead time | Delivery consideration
Cooling towers | 6–19 weeks | Cooling configuration and installation window
Air-cooled chillers | 3–49 weeks | Duty, redundancy and manufacturer selection
Water-cooled chillers | 12–60 weeks | Cooling-system design and commissioning
Air handling units | 8–78 weeks | Custom specification and controls integration
Generators | 28–66 weeks | Rating, approvals and site installation
Low-voltage switchgear | 26–58 weeks | Electrical design and approved submittals
Medium-voltage switchgear | 28–48 weeks | Utility interface and technical specification
UPS | 16–42 weeks | Power architecture and testing requirements
Notes: https://sourceblue.com/equipment-cost-index/q2-2026-cost-index-report
Underlying report: https://sourceblue.blob.core.windows.net/qa-sourceblue/uploads/media/1786376580684-59991e4c8f932e82.pdf
These are external procurement benchmarks, not assumed project durations or observed Alberta delivery commitments. Ranges vary by product and manufacturer. Confirm release-to-manufacture basis, freight, testing and installation before building a project schedule. No weeks of project delay are calculated.

## Slide 12
Three decisions would turn the screen into a delivery response
Proposed direction for the ADM, Infrastructure.
Proposed responsibilities and deadlines, subject to ADM direction
12
Decision requested | Accountable lead | Return to the ADM
Authorize a 30-day review of uncommitted capital packages | Infrastructure capital planning | Cost-weighted exposure and contingency recommendation
Direct a 60-day switchgear and chiller procurement review | Infrastructure project delivery / procurement | Release dates, alternatives and early-order business cases
Establish a power and workforce coordination table | Infrastructure with T&I, utilities and AESO | Power-on dates and a regional workforce plan
No blanket contingency uplift today. Bring back a scoped funding decision after the exposure review.
Notes: These are proposed decisions, not existing mandates, approved funding or assigned commitments. The capital review should distinguish contract-protected spend, allowances already held and genuinely uncommitted exposure. Early orders require stable designs, procurement authority, cancellation terms and a costed business case. Coordinate facility timelines without assuming AESO has responsibility for every distribution connection. Training and contractor participation require agreement; no outreach has occurred.

## Slide 13
Method and interpretation
One evidence base, with three distinct uses.
Detailed calculations and source references appear in the relevant slide notes.
13
Use | Calculation / evidence | Interpretation
Observed landscape | Dated project inventory, workforce stocks, price indexes, published lead times | Records and source periods remain visible
Labour sizing | Capex × realization × construction × labour ÷ paid rate × trade share ÷ hours ÷ years | Low/high analyst cases; gross average workload
Budget sensitivity | Capital plan × exposed share × price movement | Budget stress; no causal AI premium
Project and power exposure | Named Infrastructure developer, reported schedules, AESO process evidence | Screen for confirmation; no inferred critical-path delay
Notes: Labour assumptions: realization 25–75%, construction share 30–50%, labour share 30–40%, loaded paid-hour cost $100 low / $80 high, 20% electrician and 10% HVAC payroll shares, 1,840 paid hours/FTE-year, five years. These are not empirical productivity estimates. Lower capex realization does not imply lower hourly cost, hence the deliberately conservative paired bounds. Sensitivities are not confidence intervals. Budget 25% exposure is illustrative, and component tests are alternatives rather than additive. Do not double count observed inflation already incorporated in budgets. No measured peak, labour shortage, material quantity or causal cost elasticity is claimed.

## Slide 14
Infrastructure exposure register 1
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
14
Project | Municipality | Stage / years
Alberta Surgical Initiative (02 - Calgary) | Calgary | Construction 2024–2029
Alberta Surgical Initiative (06 - Royal Alexandra Hospital) | Edmonton | Proposed 2027–2028
Alberta Surgical Initiative (07 - Sturgeon Community Hospital) | St. Albert | Proposed 2027–2028
Alberta Surgical Initiative (13 - Ponoka Hospital and Care Centre) | Ponoka | Construction 2025–2028
Alberta Surgical Initiative (14 - Fort Saskatchewan) | Fort Saskatchewan | Proposed 2026–2028
Alberta Surgical Initiative (15 - Alberta Children's Hospital) | Calgary | Construction 2026–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10797: Alberta Surgical Initiative (02 - Calgary). Developer Alberta Infrastructure; Calgary; Under Construction; 2024–2029; as of 2026-08-31.
ABMP_11374: Alberta Surgical Initiative (06 - Royal Alexandra Hospital). Developer Alberta Infrastructure; Edmonton; Proposed; 2027–2028; as of 2026-08-31.
ABMP_11500: Alberta Surgical Initiative (07 - Sturgeon Community Hospital). Developer Alberta Infrastructure; St. Albert; Proposed; 2027–2028; as of 2026-08-31.
ABMP_11380: Alberta Surgical Initiative (13 - Ponoka Hospital and Care Centre). Developer Alberta Infrastructure; Ponoka; Under Construction; 2025–2028; as of 2026-08-31.
ABMP_11381: Alberta Surgical Initiative (14 - Fort Saskatchewan). Developer Alberta Infrastructure; Fort Saskatchewan; Proposed; 2026–2028; as of 2026-08-31.
ABMP_11382: Alberta Surgical Initiative (15 - Alberta Children's Hospital). Developer Alberta Infrastructure; Calgary; Under Construction; 2026–2027; as of 2026-08-31.

## Slide 15
Infrastructure exposure register 2
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
15
Project | Municipality | Stage / years
Alberta Surgical Initiative (16 - Grey Nuns Hospital) | Edmonton | Proposed 2026–2028
Calgary Complex Needs Residential Facility | Calgary | Construction 2025–2027
Calgary Radiopharmaceutical Centre | Calgary | Construction 2025–2027
Foothills Medical Centre Power Plant Upgrade Cogeneration Initiative | Calgary | Construction 2021–2027
La Crete Maternity and Community Health Centre | Mackenzie County | Construction 2025–2028
Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (4 - Northern Lights) | Wood Buffalo | Construction 2025–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_11383: Alberta Surgical Initiative (16 - Grey Nuns Hospital). Developer Alberta Infrastructure; Edmonton; Proposed; 2026–2028; as of 2026-08-31.
ABMP_10801: Calgary Complex Needs Residential Facility. Developer Alberta Infrastructure; Calgary; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_4363: Calgary Radiopharmaceutical Centre. Developer Alberta Infrastructure; Calgary; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_2050: Foothills Medical Centre Power Plant Upgrade Cogeneration Initiative. Developer Alberta Infrastructure; Calgary; Under Construction; 2021–2027; as of 2026-08-31.
ABMP_4364: La Crete Maternity and Community Health Centre. Developer Alberta Infrastructure; Mackenzie County; Under Construction; 2025–2028; as of 2026-08-31.
ABMP_11507: Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (4 - Northern Lights). Developer Alberta Infrastructure; Wood Buffalo; Under Construction; 2025–2027; as of 2026-08-31.

## Slide 16
Infrastructure exposure register 3
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
16
Project | Municipality | Stage / years
Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (5 - Westlock) | Westlock | Proposed 2026–2028
Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (6 - Sturgeon) | St. Albert | Proposed 2027–2030
Medical Device Reprocessing (MDR) Upgrades Program - Phase 2 (1 - Misericordia Community Hospital) | Edmonton | Construction 2026–2029
Medical Device Reprocessing (MDR) Upgrades Program - Phase 2 (2 - Grey Nuns Community Hospital) | Edmonton | Construction 2026–2028
National Association of Pharmacy Regulatory Authorities Capital Program (Medicine Hat) | Medicine Hat | Construction 2026–2027
Northern Alberta Youth Recovery Centre (NAYRC) - Edmonton EYOC | Edmonton | Construction 2025–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10951: Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (5 - Westlock). Developer Alberta Infrastructure; Westlock; Proposed; 2026–2028; as of 2026-08-31.
ABMP_10952: Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (6 - Sturgeon). Developer Alberta Infrastructure; St. Albert; Proposed; 2027–2030; as of 2026-08-31.
ABMP_11366: Medical Device Reprocessing (MDR) Upgrades Program - Phase 2 (1 - Misericordia Community Hospital). Developer Alberta Infrastructure; Edmonton; Under Construction; 2026–2029; as of 2026-08-31.
ABMP_11367: Medical Device Reprocessing (MDR) Upgrades Program - Phase 2 (2 - Grey Nuns Community Hospital). Developer Alberta Infrastructure; Edmonton; Under Construction; 2026–2028; as of 2026-08-31.
ABMP_11362: National Association of Pharmacy Regulatory Authorities Capital Program (Medicine Hat). Developer Alberta Infrastructure; Medicine Hat; Under Construction; 2026–2027; as of 2026-08-31.
ABMP_11567: Northern Alberta Youth Recovery Centre (NAYRC) - Edmonton EYOC. Developer Alberta Infrastructure; Edmonton; Under Construction; 2025–2027; as of 2026-08-31.

## Slide 17
Infrastructure exposure register 4
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
17
Project | Municipality | Stage / years
Recovery Communities (10 - Grande Prairie) | Grande Prairie | Construction 2026–2028
Recovery Communities (12 - Edmonton Young Offender Centre) | Edmonton | Construction 2025–2027
Red Deer Regional Hospital - Ambulatory Building | Red Deer | Construction 2026–2029
Red Deer Regional Hospital Centre Redevelopment | Red Deer | Construction 2024–2031
University of Alberta Hospital Brain Centre - Neurosciences Intensive Care Unit (NSICU) | Edmonton | Construction 2024–2029
Barrhead Composite High School Modernization | Barrhead | Construction 2025–2028
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10957: Recovery Communities (10 - Grande Prairie). Developer Alberta Infrastructure; Grande Prairie; Under Construction; 2026–2028; as of 2026-08-31.
ABMP_11513: Recovery Communities (12 - Edmonton Young Offender Centre). Developer Alberta Infrastructure; Edmonton; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11876: Red Deer Regional Hospital - Ambulatory Building. Developer Alberta Infrastructure; Red Deer; Under Construction; 2026–2029; as of 2026-08-31.
ABMP_4050: Red Deer Regional Hospital Centre Redevelopment. Developer Alberta Infrastructure; Red Deer; Under Construction; 2024–2031; as of 2026-08-31.
ABMP_10535: University of Alberta Hospital Brain Centre - Neurosciences Intensive Care Unit (NSICU). Developer Alberta Infrastructure; Edmonton; Under Construction; 2024–2029; as of 2026-08-31.
ABMP_11464: Barrhead Composite High School Modernization. Developer Alberta Infrastructure; Barrhead; Under Construction; 2025–2028; as of 2026-08-31.

## Slide 18
Infrastructure exposure register 5
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
18
Project | Municipality | Stage / years
Breton School K-12 Modernization | Breton | Construction 2025–2027
Delton K-6 Replacement School | Edmonton | Construction 2026–2028
Ecole Heritage K-12 Modernization | Falher | Construction 2026–2027
Holy Family K-12 Replacement School (Waskatenau) | Waskatenau | Construction 2025–2027
Holy Trinity Academy (formerly St. Francis Xavier K-9 Replacement School) | Medicine Hat | Construction 2025–2027
New 7-12 Catholic and Public High School in West Edmonton | Edmonton | Construction 2026–2029
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_11429: Breton School K-12 Modernization. Developer Alberta Infrastructure; Breton; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11456: Delton K-6 Replacement School. Developer Alberta Infrastructure; Edmonton; Under Construction; 2026–2028; as of 2026-08-31.
ABMP_11459: Ecole Heritage K-12 Modernization. Developer Alberta Infrastructure; Falher; Under Construction; 2026–2027; as of 2026-08-31.
ABMP_10941: Holy Family K-12 Replacement School (Waskatenau). Developer Alberta Infrastructure; Waskatenau; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11431: Holy Trinity Academy (formerly St. Francis Xavier K-9 Replacement School). Developer Alberta Infrastructure; Medicine Hat; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11458: New 7-12 Catholic and Public High School in West Edmonton. Developer Alberta Infrastructure; Edmonton; Under Construction; 2026–2029; as of 2026-08-31.

## Slide 19
Infrastructure exposure register 6
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
19
Project | Municipality | Stage / years
New 7-12 School in Glenridding Heights (Edmonton) | Edmonton | Construction 2025–2027
New High School in West Calgary | Calgary | Construction 2025–2028
New K-5 School in Blackfalds | Blackfalds | Construction 2025–2027
New K-8 School in Bayview (SW Airdrie) | Airdrie | Construction 2026–2028
New K-8 School in Windsong (SW Airdrie) | Airdrie | Construction 2025–2027
New K-9 Catholic School in Chestermere | Chestermere | Construction 2025–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10937: New 7-12 School in Glenridding Heights (Edmonton). Developer Alberta Infrastructure; Edmonton; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11346: New High School in West Calgary. Developer Alberta Infrastructure; Calgary; Under Construction; 2025–2028; as of 2026-08-31.
ABMP_11249: New K-5 School in Blackfalds. Developer Alberta Infrastructure; Blackfalds; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11345: New K-8 School in Bayview (SW Airdrie). Developer Alberta Infrastructure; Airdrie; Under Construction; 2026–2028; as of 2026-08-31.
ABMP_11248: New K-8 School in Windsong (SW Airdrie). Developer Alberta Infrastructure; Airdrie; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11252: New K-9 Catholic School in Chestermere. Developer Alberta Infrastructure; Chestermere; Under Construction; 2025–2027; as of 2026-08-31.

## Slide 20
Infrastructure exposure register 7
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
20
Project | Municipality | Stage / years
New K-9 Nolan Hill (Calgary) | Calgary | Construction 2025–2027
New Rangeview High School | Calgary | Construction 2025–2027
New Secondary (7-12) School in Airdrie | Airdrie | Construction 2026–2027
Solution for Nanton School | Nanton | Construction 2025–2027
Solution for Rundle Heights K-9 School | Edmonton | Construction 2025–2027
Solution for École Michaelle Jean & Gabrielle Roy | Edmonton | Construction 2025–2028
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10932: New K-9 Nolan Hill (Calgary). Developer Alberta Infrastructure; Calgary; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11251: New Rangeview High School. Developer Alberta Infrastructure; Calgary; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_10930: New Secondary (7-12) School in Airdrie. Developer Alberta Infrastructure; Airdrie; Under Construction; 2026–2027; as of 2026-08-31.
ABMP_11432: Solution for Nanton School. Developer Alberta Infrastructure; Nanton; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11253: Solution for Rundle Heights K-9 School. Developer Alberta Infrastructure; Edmonton; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_10933: Solution for �cole Michaelle Jean & Gabrielle Roy. Developer Alberta Infrastructure; Edmonton; Under Construction; 2025–2028; as of 2026-08-31.

## Slide 21
Infrastructure exposure register 8
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
21
Project | Municipality | Stage / years
Spruce Grove Composite High School Replacement | Spruce Grove | Construction 2025–2028
St. Kateri Elementary School (West Lethbridge) | Lethbridge | Construction 2025–2027
St. Martin de Porres High School Addition | Airdrie | Construction 2024–2028
Vera M. Welsh School Replacement | Lac la Biche County | Construction 2025–2027
Wainwright K-6 Elementary Replacement | Wainwright | Construction 2025–2027
École Good Shepherd K-9 Replacement | Okotoks | Construction 2025–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10940: Spruce Grove Composite High School Replacement. Developer Alberta Infrastructure; Spruce Grove; Under Construction; 2025–2028; as of 2026-08-31.
ABMP_11056: St. Kateri Elementary School (West Lethbridge). Developer Alberta Infrastructure; Lethbridge; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_4503: St. Martin de Porres High School Addition. Developer Alberta Infrastructure; Airdrie; Under Construction; 2024–2028; as of 2026-08-31.
ABMP_11410: Vera M. Welsh School Replacement. Developer Alberta Infrastructure; Lac la Biche County; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11343: Wainwright K-6 Elementary Replacement. Developer Alberta Infrastructure; Wainwright; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_10942: �cole Good Shepherd K-9 Replacement. Developer Alberta Infrastructure; Okotoks; Under Construction; 2025–2027; as of 2026-08-31.

## Slide 22
Infrastructure exposure register 9
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
22
Project | Municipality | Stage / years
École Mallaig K-12 Replacement School | St. Paul County No. 19 | Construction 2025–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_11256: �cole Mallaig K-12 Replacement School. Developer Alberta Infrastructure; St. Paul County No. 19; Under Construction; 2025–2027; as of 2026-08-31.

## Slide 23
Alberta pipeline reference 1 of 3
Full identified core project and phase records.
Alberta Major Projects, 31 Aug 2026. ? = missing year; — = missing cost. Estimated scope varies.
23
Project / phase | Stage | Reported years | CAD B
eStruxture CAL-3 Data Centre | Construction | 2024–2026 | 0.75
Wonder Valley AI Data Centre Park (Phase 1) | Proposed | ?–? | 12.00
Beacon Foothills AI Data Centre Hub | Proposed | ?–? | 4.00
Beacon Harry Smith AI Data Centre Hub | Proposed | ?–? | —
Beacon Indus Data Centre Hub | Proposed | ?–? | —
Beacon Heartland AI Data Centre Hub | Proposed | ?–2027 | —
Beacon Saunders Lake AI Data Centre Hub | Proposed | ?–? | —
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Names and reported values are preserved from the dated inventory. “Construction” abbreviates the publisher’s “Under Construction” status. Start and end years are reported years without back-calculation. These records are not a confirmed delivery forecast.
eStruxture CAL-3 Data Centre: https://info.estruxture.com/hubfs/Data%20Sheets/eStruxture_Datasheet_CAL3%20EN%20V2%202025.pdf?__hstc=17468411.9cbf58fbaac1d56717987d205a46139e.1778703431220.1778703431220.1778703431220.1&__hssc=17468411.4.1779463158036&__hsfp=31c185fa9baa393ca4363973b4df6c18
Wonder Valley AI Data Centre Park (Phase 1): https://www.olearydigital.ai/
Beacon Harry Smith AI Data Centre Hub: https://beacondatacenters.com/campuses/
Beacon Indus Data Centre Hub: https://beacondatacenters.com/wp-content/uploads/2026/02/BEA_IndusCGY-FAQ.pdf
Beacon Heartland AI Data Centre Hub: https://beacondatacenters.com/campuses/
Beacon Saunders Lake AI Data Centre Hub: https://beacondatacenters.com/campuses/

## Slide 24
Alberta pipeline reference 2 of 3
Full identified core project and phase records.
Alberta Major Projects, 31 Aug 2026. ? = missing year; — = missing cost. Estimated scope varies.
24
Project / phase | Stage | Reported years | CAD B
Crusoe AI Data Centres Alberta | Proposed | ?–? | 3.00
HubOne AI & BTC High Density Compute Park | Proposed | ?–? | —
Prairie Sky Data Solutions Strathmore Data Center (Phase 1) | Proposed | ?–2026 | —
eStruxture CAL-1 Data Centre - Phase 4 Alterations | Construction | 2025–? | —
Blindman Industrial Park AI Data Centre | Construction | 2026–2026 | —
Technologies New Energy & Data District Data Centres (Phase 1) | Proposed | 2026–? | 1.26
Data Centre (Clive) | Proposed | 2026–? | —
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Names and reported values are preserved from the dated inventory. “Construction” abbreviates the publisher’s “Under Construction” status. Start and end years are reported years without back-calculation. These records are not a confirmed delivery forecast.
HubOne AI & BTC High Density Compute Park: https://hub1.ca/
Prairie Sky Data Solutions Strathmore Data Center (Phase 1): https://www.prairieskydata.com/

## Slide 25
Alberta pipeline reference 3 of 3
Full identified core project and phase records.
Alberta Major Projects, 31 Aug 2026. ? = missing year; — = missing cost. Estimated scope varies.
25
Project / phase | Stage | Reported years | CAD B
Mihta Askiy Data Centre | Proposed | 2027–? | —
Beacon Chestermere AI Data Centre Hub | Proposed | ?–2027 | —
K-Tech and Aurora AZ Energy Compute Facility | Construction | 2026–? | —
Meta Data Centre | Proposed | ?–? | 13.00
Malachite One Data Centre | Proposed | 2027–2030 | 15.00
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Names and reported values are preserved from the dated inventory. “Construction” abbreviates the publisher’s “Under Construction” status. Start and end years are reported years without back-calculation. These records are not a confirmed delivery forecast.
Beacon Chestermere AI Data Centre Hub: https://beacondatacenters.com/campuses/