## Slide 1
Alberta data centres
Capital exposure and decisions for Infrastructure
September 2026
Notes: Independent analysis. Colour reference: https://www.alberta.ca/colour-palette. Government of Alberta blue, sky and prairie palette. No government endorsement implied. Project snapshot 31 August 2026. Source dates are retained on each evidence slide.

## Slide 2
A proposed pipeline meets an active construction market
19 identified data-centre records sit alongside substantial infrastructure investment.
Sources: Alberta Major Projects, 31 Aug 2026; Alberta first-quarter fiscal update, 2026–27
2
Chart: 
| Proposed | Under construction
Data-centre records | 15 | 4
$10.687B
Updated Alberta capital plan for FY2026–27
Shared trades and suppliers create potential competition as projects advance.
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
https://open.alberta.ca/dataset/9c81a5a7-cdf1-49ad-a923-d1ecb42944e4/resource/eaeb7a75-0c9f-4964-be53-0f1cc889ffab/download/tbf-2026-27-first-quarter-fiscal-update-economic-statement.pdf
The 19 core records can represent phases or multi-location programmes, rather than unique campuses. Three enabling power records are separate. Proposed status does not establish financing, procurement or construction start. The capital plan spans different asset classes and includes more than construction labour.

## Slide 3
Seven reported projects account for $49.01B
Reported investment estimates, CAD billions.
Source: Alberta Major Projects, 31 Aug 2026. Twelve additional core records have no reported cost.
3
Chart: CAD billions
| Malachite One | Meta | Wonder Valley P1 | Beacon Foothills | Crusoe Alberta | TNE Data District P1 | eStruxture CAL-3
Reported CAD billions | 15 | 13 | 12 | 4 | 3 | 1.26 | 0.75
Construction-only scope is bracketed in the labour sizing scenario.
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Seven core estimated costs sum to CAD49.01B. The other 12 core records lack costs. The sum excludes CAD6.40B from three enabling power records. Amounts may include servers, land and enabling works. The separate project model uses explicit construction and labour coefficients. Names are shortened on the chart; the appendix carries the full record names.

## Slide 4
Demand concentrates in shared construction packages
Civil works establish the site. Electrical and cooling systems drive specialist fit-out.
Engineering scope classification; actual crew and supplier overlap depends on package timing and location.
4
Package | Labour demand | Materials and equipment
Civil / structural | Operators, labourers, formwork crews, finishers, ironworkers | Concrete, aggregate, reinforcing and structural steel
Electrical | Electricians, cable installers, controls and testing specialists | Transformers, switchgear, cable, UPS and generators
Mechanical / cooling | HVAC and sheet-metal workers, pipefitters, plumbers, insulators | Chillers, air handlers, pumps, pipework and ducts
Utility connections | Line crews, utility engineers and enabling civil crews | Substations, connection equipment and utility corridors
Notes: Engineering interpretation of typical data-centre construction packages. The table identifies shared resources, not measured project quantities or incremental Alberta job demand. Site location, cooling design, electrical architecture and prefabrication determine the final scope. Electrical utility connections and permitting can be separate from the building contract.

## Slide 5
2029 is a scheduling stress case, not a forecast
Annual electrician FTE: four undated phases represent $32B of the $49B pipeline.
Central intensity, full realization. Reported year anchors can still require inferred endpoints.
5
Chart: 
| 2027 | 2028 | 2029 | 2030 | 2031 | 2032
Reported year anchor | 28.6396 | 710.6042 | 1446.4245 | 563.6071 | 0 | 0
Fully fallback-scheduled | 0 | 14.844 | 2493.7874 | 2842.6208 | 59.3759 | 0
Common March 2028 starts concentrate the undated cohort. Timing and realization tests follow.
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
50% is a uniform volume reduction on proposed projects, not a calibrated probability or a selected half of projects. Construction-stage volumes are retained. The 48-month case changes only wholly undated durations. Reported anchors can still require inferred endpoints. Historical workforce ratios are scale comparisons, not available capacity.
Trade hours = cost × construction share × labour share / loaded paid-hour cost × trade payroll share. Monthly triangular weights conserve trade hours; annual FTE = hours / 1840. Four fully undated records use evidence month + 18 months and 36 months. Three records have at least one reported year anchor; these are not wholly observed construction schedules. The fall after completion is a cohort effect, not no future demand.

## Slide 6
HVAC demand reaches 62% of historical workforce scale
Electricians reach 29% in the full-realization, 36-month stress case.
Durations vary only for undated phases. Annual FTE / May 2021 stock measures scale, not available capacity.
6
Central-intensity test | Electricians: peak / stock | HVAC: peak / stock
Full realization / 36 months | 3,940 (29%) · 2029 | 1,926 (62%) · 2030
50% proposed volume / 36 months | 1,970 (15%) · 2029 | 963 (31%) · 2030
Full realization / 48 months | 3,503 (26%) · 2030 | 1,813 (59%) · 2030
Historical stocks: 13,375 electricians; 3,095 HVAC mechanics. Other capital projects also draw on these trades.
Notes: Statistics Canada, Alberta observations. Census Table 98-10-0449-01, May 2021 employed persons: https://www150.statcan.gc.ca/t1/tbl1/en/tv.action?pid=9810044901
Job Vacancy and Wage Survey, Table 14-10-0444-01, Q1 2026: https://www150.statcan.gc.ca/t1/tbl1/en/tv.action?pid=1410044401
50% is a uniform volume reduction on proposed projects, not a calibrated probability or a selected half of projects. Construction-stage volumes are retained. The 48-month case changes only wholly undated durations. Reported anchors can still require inferred endpoints. Historical workforce ratios are scale comparisons, not available capacity.
Full realization / 36 months: electrical 3,940 FTE in 2029; HVAC 1,926 FTE in 2030.
50% proposed volume / 36 months: electrical 1,970 FTE in 2029; HVAC 963 FTE in 2030.
Full realization / 48 months: electrical 3,503 FTE in 2030; HVAC 1,813 FTE in 2030.
The 48-month sensitivity changes only the four wholly undated phases; Malachite retains its reported 2027–2030 window. 50% realization means half the proposed volume at each date, not a random project selection. Low/high intensity parameters remain in the model, separate from realization.

## Slide 7
HVAC and steel prices show the largest increases
Calgary and Edmonton industrial-factory construction components, Q2 2026 versus Q2 2025.
Source: Statistics Canada, Table 18-10-0289-01. Contractor bid-price changes, not raw-material prices.
7
Chart: 
| Concrete | Structural steel | Electrical systems | HVAC
Calgary | 4.11 | 7.3 | 0.83 | 10.05
Edmonton | 5.24 | 10.44 | 1.01 | 10.05
HVAC and steel warrant a cost-weighted procurement review.
Notes: Statistics Canada, Building construction price indexes, Table 18-10-0289-01, Calgary and Edmonton industrial-factory components, Q2 2026 year-over-year changes. https://www150.statcan.gc.ca/t1/tbl1/en/tv.action?pid=1810028901
Year-over-year component changes from the industrial-factory archetype. It is a proxy for construction cost conditions, not a data-centre construction price index. Figures do not measure physical material volumes or supplier spare capacity, nor identify the causal contribution of data-centre activity.

## Slide 8
Every $1B of scope carries $25M in this sensitivity
10% price shock on 25% exposed scope; Infrastructure’s envelope requires confirmation.
Each row is a separate exposure test. Do not add them or layer them onto an escalated baseline.
8
Price movement | Calgary / Edmonton | 25% of provincial $10.687B plan
Concrete | 4.11% / 5.24% | $110M / $140M
Structural steel | 7.30% / 10.44% | $195M / $279M
Electrical systems | 0.83% / 1.01% | $22M / $27M
HVAC | 10.05% / 10.05% | $269M / $268M
Provincial illustration: $267M. Apply $25M per $1B to Infrastructure’s confirmed uncommitted scope.
Notes: Statistics Canada, Building construction price indexes, Table 18-10-0289-01, Calgary and Edmonton industrial-factory components, Q2 2026 year-over-year changes. https://www150.statcan.gc.ca/t1/tbl1/en/tv.action?pid=1810028901
https://open.alberta.ca/dataset/9c81a5a7-cdf1-49ad-a923-d1ecb42944e4/resource/eaeb7a75-0c9f-4964-be53-0f1cc889ffab/download/tbf-2026-27-first-quarter-fiscal-update-economic-statement.pdf
Exposure share is an analyst assumption, not measured capital-plan composition. Impact = $10,687M × exposed share × observed YoY percentage/100. Each row assumes the same quarter of the plan independently exposed to that component movement. No rows are summed. The historical movement is applied as a stress, not a future forecast or AI-attributable premium. Use uncommitted scope, contract allocation of price risk and current baseline price date before reserving contingency. 1% of whole plan = $106.87M; 10% = $1,068.7M. The plan is consolidated provincial capital, not the Infrastructure ministry budget alone.

## Slide 9
Seven Infrastructure records intersect 2029–2030
Regional screen against the full-realization scheduling stress window.
Reported project windows, not confirmed package dates or shared contractors. Full register in the appendix.
9
Infrastructure project | Municipality / end | Regional DC screen
ASI Calgary | Calgary / 2029 | Beacon / Crusoe / TNE
Sturgeon MDR | St. Albert / 2030 | Meta Sturgeon / TNE
Misericordia MDR | Edmonton / 2029 | Meta Sturgeon / TNE
Red Deer ambulatory building | Red Deer / 2029 | Crusoe Red Deer
Red Deer hospital redevelopment | Red Deer / 2031 | Crusoe Red Deer
UAH neurosciences ICU | Edmonton / 2029 | Meta Sturgeon / TNE
West Edmonton high school | Edmonton / 2029 | Meta Sturgeon / TNE
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
Filter: developer Alberta Infrastructure; reported start <=2030 and end >=2029. Seven of the 49 known 2027–2036 overlaps. Packages to confirm: electrical fit-out, cooling and commissioning. Municipal proximity is an analytical screen, not a verified labour catchment. Calgary pairs with Beacon Foothills, Crusoe Rocky View and TNE Calgary; Red Deer with Crusoe Red Deer; Edmonton/St Albert with Meta Sturgeon and TNE Edmonton. Multi-location programme costs are not allocated between municipalities. No matching northwest record in this seven-record subset is inferred for Wonder Valley.
Alberta Surgical Initiative (02 - Calgary): 2024–2029; Under Construction
Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (6 - Sturgeon): 2027–2030; Proposed
Medical Device Reprocessing (MDR) Upgrades Program - Phase 2 (1 - Misericordia Community Hospital): 2026–2029; Under Construction
Red Deer Regional Hospital - Ambulatory Building: 2026–2029; Under Construction
Red Deer Regional Hospital Centre Redevelopment: 2024–2031; Under Construction
University of Alberta Hospital Brain Centre - Neurosciences Intensive Care Unit (NSICU): 2024–2029; Under Construction
New 7-12 Catholic and Public High School in West Edmonton: 2026–2029; Under Construction

## Slide 10
Power belongs in the delivery conversation
Three enabling-power proposals total $6.4B, separate from the core data-centre pipeline.
Sources: Alberta Major Projects, 31 Aug 2026; AESO large-load page checked 6 Sep 2026
10
Enabling-power proposal | Municipality | MW / reported end
Greenlight Electricity Centre | Sturgeon County | 932 MW / 2030
Teton Digital Black Bear Power Project | Swan Hills | 466 MW / 2028
Teton Digital Northern Forge Power Project | Greenview No. 16 | 200 MW / 2028
AESO Phase 1: 1,200 MW allocated to executed load contracts.
Infrastructure needs facility-level power-on milestones from AESO and local utilities.
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Greenlight Electricity Centre: https://greenlightelectricitycentre.ca/
Teton Digital Black Bear Power Project: https://www.tetondigital.io/black-bear
Teton Digital Northern Forge Power Project: https://www.tetondigital.io/northern-forge
https://www.aeso.ca/grid/connecting-to-the-grid/large-load-projects/
AESO checked 6 September 2026: Phase 1 allocates 970 MW to GLDC Load and 230 MW to Keephills Data Centre Phase I. The projects continue through the Connection Process. Phase 2A is a BYOG process. Executed contracts do not mean energized load. Generation proposals total 1,598 MW, distinct from load contracts and not a measure of spare network capacity. Their data-centre-enabling classification is analytical. No inference of a province-wide transmission shortage or a public-facility delay. Distribution service and equipment can matter independently of the large-load process.

## Slide 11
Equipment availability can govern delivery dates
Supplier lead-time benchmarks relevant to Alberta procurement planning.
SourceBlue, Q2 2026 US market ranges. Alberta delivery requires a product-specific supplier quotation.
11
Equipment | Published lead time | Delivery consideration
Cooling towers | 6–19 weeks | Cooling configuration and installation window
Air-cooled chillers | 3–49 weeks | Duty, redundancy and manufacturer selection
Water-cooled chillers | 12–60 weeks | Cooling-system design and commissioning
Air handling units | 8–78 weeks | Custom specification and controls integration
Generators | 28–66 weeks | Rating, approvals and site installation
Low-voltage switchgear | 26–58 weeks | Electrical design and approved submittals
Medium-voltage switchgear | 28–48 weeks | Utility interface and technical specification
UPS | 16–42 weeks | Power architecture and testing requirements
Notes: https://sourceblue.com/equipment-cost-index/q2-2026-cost-index-report
Underlying report: https://sourceblue.blob.core.windows.net/qa-sourceblue/uploads/media/1786376580684-59991e4c8f932e82.pdf
These are external procurement benchmarks, not assumed project durations or observed Alberta delivery commitments. Ranges vary by product and manufacturer. Confirm release-to-manufacture basis, freight, testing and installation before building a project schedule. No weeks of project delay are calculated.

## Slide 12
Three decisions would turn the screen into a delivery response
Proposed direction for the ADM, Infrastructure.
Proposed responsibilities and deadlines, subject to ADM direction
12
Decision requested | Accountable lead | Return to the ADM
Authorize a 30-day review of uncommitted capital packages | Infrastructure capital planning | Cost-weighted exposure and contingency recommendation
Direct a 60-day switchgear and chiller procurement review | Infrastructure project delivery / procurement | Release dates, alternatives and early-order business cases
Establish a power and workforce coordination table | Infrastructure with T&I, utilities and AESO | Power-on dates and a regional workforce plan
No blanket contingency uplift today. Bring back a scoped funding decision after the exposure review.
Notes: These are proposed decisions, not existing mandates, approved funding or assigned commitments. The capital review should distinguish contract-protected spend, allowances already held and genuinely uncommitted exposure. Early orders require stable designs, procurement authority, cancellation terms and a costed business case. Coordinate facility timelines without assuming AESO has responsibility for every distribution connection. Training and contractor participation require agreement; no outreach has occurred.

## Slide 13
Method and interpretation
One evidence base, with three distinct uses.
Detailed calculations and source references appear in the relevant slide notes.
13
Use | Calculation / evidence | Interpretation
Observed landscape | Dated project inventory, workforce stocks, price indexes, published lead times | Records and source periods remain visible
Labour demand model | Project trade hours × monthly work-profile weights ÷ annual paid hours | Schedule-resolved conditional model; low / central / high intensity
Budget sensitivity | Capital plan × exposed share × price movement | Budget stress; no causal AI premium
Project and power exposure | Named Infrastructure developer, reported schedules, AESO process evidence | Screen for confirmation; no inferred critical-path delay
Notes: Model coefficients: construction share 30/40/50%, labour share 30/35/40%, loaded hourly cost $100/$90/$80, electrician/HVAC payroll shares 20/10%, 1840 paid hours per FTE-year. Each project retains reported dates and explicitly inferred endpoints or assigned starts. Undated start = evidence month + 18 months, default duration 36 months, triangular work curves. Full, 50% proposed-volume and 48-month undated-duration sensitivities. No calibrated probabilities, spare capacity or causal cost elasticity. Budget sensitivities remain separate from labour demand.