## Slide 1
Project model schedule register 1
Reported fields remain unchanged. The model retains a separate schedule basis.
Model-assigned dates are planning inputs and do not establish developer commitments.
1
Costed phase | Model start / finish | Schedule basis
eStruxture CAL-3 Data Centre | 2024-01 / 2026-12 | Reported start/end years; January/December conventions
Wonder Valley AI Data Centre Park (Phase 1) | 2028-03 / 2031-02 | Model-assigned start: as-of + 18 months; 36-month duration
Beacon Foothills AI Data Centre Hub | 2028-03 / 2031-02 | Model-assigned start: as-of + 18 months; 36-month duration
Crusoe AI Data Centres Alberta | 2028-03 / 2031-02 | Model-assigned start: as-of + 18 months; 36-month duration
Technologies New Energy & Data District Data Centres (Phase 1) | 2026-09 / 2029-08 | Reported start year; model-inferred end from 36-month duration; past proposed start shifted to as-of month
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
eStruxture CAL-3 Data Centre: reported start 2024, reported end 2026, model start 2024-01, model finish 2026-12; Reported start/end years; January/December conventions
Wonder Valley AI Data Centre Park (Phase 1): reported start missing, reported end missing, model start 2028-03, model finish 2031-02; Model-assigned start: as-of + 18 months; 36-month duration
Beacon Foothills AI Data Centre Hub: reported start missing, reported end missing, model start 2028-03, model finish 2031-02; Model-assigned start: as-of + 18 months; 36-month duration
Crusoe AI Data Centres Alberta: reported start missing, reported end missing, model start 2028-03, model finish 2031-02; Model-assigned start: as-of + 18 months; 36-month duration
Technologies New Energy & Data District Data Centres (Phase 1): reported start 2026, reported end missing, model start 2026-09, model finish 2029-08; Reported start year; model-inferred end from 36-month duration; past proposed start shifted to as-of month

## Slide 2
Project model schedule register 2
Reported fields remain unchanged. The model retains a separate schedule basis.
Model-assigned dates are planning inputs and do not establish developer commitments.
2
Costed phase | Model start / finish | Schedule basis
Meta Data Centre | 2028-03 / 2031-02 | Model-assigned start: as-of + 18 months; 36-month duration
Malachite One Data Centre | 2027-01 / 2030-12 | Reported start/end years; January/December conventions
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Meta Data Centre: reported start missing, reported end missing, model start 2028-03, model finish 2031-02; Model-assigned start: as-of + 18 months; 36-month duration
Malachite One Data Centre: reported start 2027, reported end 2030, model start 2027-01, model finish 2030-12; Reported start/end years; January/December conventions

## Slide 3
Infrastructure exposure register 1
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
3
Project | Municipality | Stage / years
Alberta Surgical Initiative (02 - Calgary) | Calgary | Construction 2024–2029
Alberta Surgical Initiative (06 - Royal Alexandra Hospital) | Edmonton | Proposed 2027–2028
Alberta Surgical Initiative (07 - Sturgeon Community Hospital) | St. Albert | Proposed 2027–2028
Alberta Surgical Initiative (13 - Ponoka Hospital and Care Centre) | Ponoka | Construction 2025–2028
Alberta Surgical Initiative (14 - Fort Saskatchewan) | Fort Saskatchewan | Proposed 2026–2028
Alberta Surgical Initiative (15 - Alberta Children's Hospital) | Calgary | Construction 2026–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10797: Alberta Surgical Initiative (02 - Calgary). Developer Alberta Infrastructure; Calgary; Under Construction; 2024–2029; as of 2026-08-31.
ABMP_11374: Alberta Surgical Initiative (06 - Royal Alexandra Hospital). Developer Alberta Infrastructure; Edmonton; Proposed; 2027–2028; as of 2026-08-31.
ABMP_11500: Alberta Surgical Initiative (07 - Sturgeon Community Hospital). Developer Alberta Infrastructure; St. Albert; Proposed; 2027–2028; as of 2026-08-31.
ABMP_11380: Alberta Surgical Initiative (13 - Ponoka Hospital and Care Centre). Developer Alberta Infrastructure; Ponoka; Under Construction; 2025–2028; as of 2026-08-31.
ABMP_11381: Alberta Surgical Initiative (14 - Fort Saskatchewan). Developer Alberta Infrastructure; Fort Saskatchewan; Proposed; 2026–2028; as of 2026-08-31.
ABMP_11382: Alberta Surgical Initiative (15 - Alberta Children's Hospital). Developer Alberta Infrastructure; Calgary; Under Construction; 2026–2027; as of 2026-08-31.

## Slide 4
Infrastructure exposure register 2
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
4
Project | Municipality | Stage / years
Alberta Surgical Initiative (16 - Grey Nuns Hospital) | Edmonton | Proposed 2026–2028
Calgary Complex Needs Residential Facility | Calgary | Construction 2025–2027
Calgary Radiopharmaceutical Centre | Calgary | Construction 2025–2027
Foothills Medical Centre Power Plant Upgrade Cogeneration Initiative | Calgary | Construction 2021–2027
La Crete Maternity and Community Health Centre | Mackenzie County | Construction 2025–2028
Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (4 - Northern Lights) | Wood Buffalo | Construction 2025–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_11383: Alberta Surgical Initiative (16 - Grey Nuns Hospital). Developer Alberta Infrastructure; Edmonton; Proposed; 2026–2028; as of 2026-08-31.
ABMP_10801: Calgary Complex Needs Residential Facility. Developer Alberta Infrastructure; Calgary; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_4363: Calgary Radiopharmaceutical Centre. Developer Alberta Infrastructure; Calgary; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_2050: Foothills Medical Centre Power Plant Upgrade Cogeneration Initiative. Developer Alberta Infrastructure; Calgary; Under Construction; 2021–2027; as of 2026-08-31.
ABMP_4364: La Crete Maternity and Community Health Centre. Developer Alberta Infrastructure; Mackenzie County; Under Construction; 2025–2028; as of 2026-08-31.
ABMP_11507: Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (4 - Northern Lights). Developer Alberta Infrastructure; Wood Buffalo; Under Construction; 2025–2027; as of 2026-08-31.

## Slide 5
Infrastructure exposure register 3
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
5
Project | Municipality | Stage / years
Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (5 - Westlock) | Westlock | Proposed 2026–2028
Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (6 - Sturgeon) | St. Albert | Proposed 2027–2030
Medical Device Reprocessing (MDR) Upgrades Program - Phase 2 (1 - Misericordia Community Hospital) | Edmonton | Construction 2026–2029
Medical Device Reprocessing (MDR) Upgrades Program - Phase 2 (2 - Grey Nuns Community Hospital) | Edmonton | Construction 2026–2028
National Association of Pharmacy Regulatory Authorities Capital Program (Medicine Hat) | Medicine Hat | Construction 2026–2027
Northern Alberta Youth Recovery Centre (NAYRC) - Edmonton EYOC | Edmonton | Construction 2025–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10951: Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (5 - Westlock). Developer Alberta Infrastructure; Westlock; Proposed; 2026–2028; as of 2026-08-31.
ABMP_10952: Medical Device Reprocessing (MDR) Upgrades Program - Phase 1 (6 - Sturgeon). Developer Alberta Infrastructure; St. Albert; Proposed; 2027–2030; as of 2026-08-31.
ABMP_11366: Medical Device Reprocessing (MDR) Upgrades Program - Phase 2 (1 - Misericordia Community Hospital). Developer Alberta Infrastructure; Edmonton; Under Construction; 2026–2029; as of 2026-08-31.
ABMP_11367: Medical Device Reprocessing (MDR) Upgrades Program - Phase 2 (2 - Grey Nuns Community Hospital). Developer Alberta Infrastructure; Edmonton; Under Construction; 2026–2028; as of 2026-08-31.
ABMP_11362: National Association of Pharmacy Regulatory Authorities Capital Program (Medicine Hat). Developer Alberta Infrastructure; Medicine Hat; Under Construction; 2026–2027; as of 2026-08-31.
ABMP_11567: Northern Alberta Youth Recovery Centre (NAYRC) - Edmonton EYOC. Developer Alberta Infrastructure; Edmonton; Under Construction; 2025–2027; as of 2026-08-31.

## Slide 6
Infrastructure exposure register 4
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
6
Project | Municipality | Stage / years
Recovery Communities (10 - Grande Prairie) | Grande Prairie | Construction 2026–2028
Recovery Communities (12 - Edmonton Young Offender Centre) | Edmonton | Construction 2025–2027
Red Deer Regional Hospital - Ambulatory Building | Red Deer | Construction 2026–2029
Red Deer Regional Hospital Centre Redevelopment | Red Deer | Construction 2024–2031
University of Alberta Hospital Brain Centre - Neurosciences Intensive Care Unit (NSICU) | Edmonton | Construction 2024–2029
Barrhead Composite High School Modernization | Barrhead | Construction 2025–2028
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10957: Recovery Communities (10 - Grande Prairie). Developer Alberta Infrastructure; Grande Prairie; Under Construction; 2026–2028; as of 2026-08-31.
ABMP_11513: Recovery Communities (12 - Edmonton Young Offender Centre). Developer Alberta Infrastructure; Edmonton; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11876: Red Deer Regional Hospital - Ambulatory Building. Developer Alberta Infrastructure; Red Deer; Under Construction; 2026–2029; as of 2026-08-31.
ABMP_4050: Red Deer Regional Hospital Centre Redevelopment. Developer Alberta Infrastructure; Red Deer; Under Construction; 2024–2031; as of 2026-08-31.
ABMP_10535: University of Alberta Hospital Brain Centre - Neurosciences Intensive Care Unit (NSICU). Developer Alberta Infrastructure; Edmonton; Under Construction; 2024–2029; as of 2026-08-31.
ABMP_11464: Barrhead Composite High School Modernization. Developer Alberta Infrastructure; Barrhead; Under Construction; 2025–2028; as of 2026-08-31.

## Slide 7
Infrastructure exposure register 5
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
7
Project | Municipality | Stage / years
Breton School K-12 Modernization | Breton | Construction 2025–2027
Delton K-6 Replacement School | Edmonton | Construction 2026–2028
Ecole Heritage K-12 Modernization | Falher | Construction 2026–2027
Holy Family K-12 Replacement School (Waskatenau) | Waskatenau | Construction 2025–2027
Holy Trinity Academy (formerly St. Francis Xavier K-9 Replacement School) | Medicine Hat | Construction 2025–2027
New 7-12 Catholic and Public High School in West Edmonton | Edmonton | Construction 2026–2029
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_11429: Breton School K-12 Modernization. Developer Alberta Infrastructure; Breton; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11456: Delton K-6 Replacement School. Developer Alberta Infrastructure; Edmonton; Under Construction; 2026–2028; as of 2026-08-31.
ABMP_11459: Ecole Heritage K-12 Modernization. Developer Alberta Infrastructure; Falher; Under Construction; 2026–2027; as of 2026-08-31.
ABMP_10941: Holy Family K-12 Replacement School (Waskatenau). Developer Alberta Infrastructure; Waskatenau; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11431: Holy Trinity Academy (formerly St. Francis Xavier K-9 Replacement School). Developer Alberta Infrastructure; Medicine Hat; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11458: New 7-12 Catholic and Public High School in West Edmonton. Developer Alberta Infrastructure; Edmonton; Under Construction; 2026–2029; as of 2026-08-31.

## Slide 8
Infrastructure exposure register 6
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
8
Project | Municipality | Stage / years
New 7-12 School in Glenridding Heights (Edmonton) | Edmonton | Construction 2025–2027
New High School in West Calgary | Calgary | Construction 2025–2028
New K-5 School in Blackfalds | Blackfalds | Construction 2025–2027
New K-8 School in Bayview (SW Airdrie) | Airdrie | Construction 2026–2028
New K-8 School in Windsong (SW Airdrie) | Airdrie | Construction 2025–2027
New K-9 Catholic School in Chestermere | Chestermere | Construction 2025–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10937: New 7-12 School in Glenridding Heights (Edmonton). Developer Alberta Infrastructure; Edmonton; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11346: New High School in West Calgary. Developer Alberta Infrastructure; Calgary; Under Construction; 2025–2028; as of 2026-08-31.
ABMP_11249: New K-5 School in Blackfalds. Developer Alberta Infrastructure; Blackfalds; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11345: New K-8 School in Bayview (SW Airdrie). Developer Alberta Infrastructure; Airdrie; Under Construction; 2026–2028; as of 2026-08-31.
ABMP_11248: New K-8 School in Windsong (SW Airdrie). Developer Alberta Infrastructure; Airdrie; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11252: New K-9 Catholic School in Chestermere. Developer Alberta Infrastructure; Chestermere; Under Construction; 2025–2027; as of 2026-08-31.

## Slide 9
Infrastructure exposure register 7
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
9
Project | Municipality | Stage / years
New K-9 Nolan Hill (Calgary) | Calgary | Construction 2025–2027
New Rangeview High School | Calgary | Construction 2025–2027
New Secondary (7-12) School in Airdrie | Airdrie | Construction 2026–2027
Solution for Nanton School | Nanton | Construction 2025–2027
Solution for Rundle Heights K-9 School | Edmonton | Construction 2025–2027
Solution for École Michaelle Jean & Gabrielle Roy | Edmonton | Construction 2025–2028
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10932: New K-9 Nolan Hill (Calgary). Developer Alberta Infrastructure; Calgary; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11251: New Rangeview High School. Developer Alberta Infrastructure; Calgary; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_10930: New Secondary (7-12) School in Airdrie. Developer Alberta Infrastructure; Airdrie; Under Construction; 2026–2027; as of 2026-08-31.
ABMP_11432: Solution for Nanton School. Developer Alberta Infrastructure; Nanton; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11253: Solution for Rundle Heights K-9 School. Developer Alberta Infrastructure; Edmonton; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_10933: Solution for École Michaelle Jean & Gabrielle Roy. Developer Alberta Infrastructure; Edmonton; Under Construction; 2025–2028; as of 2026-08-31.

## Slide 10
Infrastructure exposure register 8
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
10
Project | Municipality | Stage / years
Spruce Grove Composite High School Replacement | Spruce Grove | Construction 2025–2028
St. Kateri Elementary School (West Lethbridge) | Lethbridge | Construction 2025–2027
St. Martin de Porres High School Addition | Airdrie | Construction 2024–2028
Vera M. Welsh School Replacement | Lac la Biche County | Construction 2025–2027
Wainwright K-6 Elementary Replacement | Wainwright | Construction 2025–2027
École Good Shepherd K-9 Replacement | Okotoks | Construction 2025–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_10940: Spruce Grove Composite High School Replacement. Developer Alberta Infrastructure; Spruce Grove; Under Construction; 2025–2028; as of 2026-08-31.
ABMP_11056: St. Kateri Elementary School (West Lethbridge). Developer Alberta Infrastructure; Lethbridge; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_4503: St. Martin de Porres High School Addition. Developer Alberta Infrastructure; Airdrie; Under Construction; 2024–2028; as of 2026-08-31.
ABMP_11410: Vera M. Welsh School Replacement. Developer Alberta Infrastructure; Lac la Biche County; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_11343: Wainwright K-6 Elementary Replacement. Developer Alberta Infrastructure; Wainwright; Under Construction; 2025–2027; as of 2026-08-31.
ABMP_10942: École Good Shepherd K-9 Replacement. Developer Alberta Infrastructure; Okotoks; Under Construction; 2025–2027; as of 2026-08-31.

## Slide 11
Infrastructure exposure register 9
Developer: Alberta Infrastructure. Known schedule overlap with 2027–2036.
Package phase and legal ownership unverified. Electrical, cooling and commissioning are screening intersections.
11
Project | Municipality | Stage / years
École Mallaig K-12 Replacement School | St. Paul County No. 19 | Construction 2025–2027
Notes: Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Analytical screen: school/postsecondary, roads/transit/airports, health, power, water/resilience and government/civic categories. Records can include private ownership. Schedule overlap does not demonstrate resource competition.
ABMP_11256: École Mallaig K-12 Replacement School. Developer Alberta Infrastructure; St. Paul County No. 19; Under Construction; 2025–2027; as of 2026-08-31.

## Slide 12
Alberta pipeline reference 1 of 3
Full identified core project and phase records.
Alberta Major Projects, 31 Aug 2026. ? = missing year; — = missing cost. Estimated scope varies.
12
Project / phase | Stage | Reported years | CAD B
eStruxture CAL-3 Data Centre | Construction | 2024–2026 | 0.75
Wonder Valley AI Data Centre Park (Phase 1) | Proposed | ?–? | 12.00
Beacon Foothills AI Data Centre Hub | Proposed | ?–? | 4.00
Beacon Harry Smith AI Data Centre Hub | Proposed | ?–? | —
Beacon Indus Data Centre Hub | Proposed | ?–? | —
Beacon Heartland AI Data Centre Hub | Proposed | ?–2027 | —
Beacon Saunders Lake AI Data Centre Hub | Proposed | ?–? | —
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Names and reported values are preserved from the dated inventory. “Construction” abbreviates the publisher’s “Under Construction” status. Start and end years are reported years without back-calculation. These records are not a confirmed delivery forecast.
eStruxture CAL-3 Data Centre: https://info.estruxture.com/hubfs/Data%20Sheets/eStruxture_Datasheet_CAL3%20EN%20V2%202025.pdf?__hstc=17468411.9cbf58fbaac1d56717987d205a46139e.1778703431220.1778703431220.1778703431220.1&__hssc=17468411.4.1779463158036&__hsfp=31c185fa9baa393ca4363973b4df6c18
Wonder Valley AI Data Centre Park (Phase 1): https://www.olearydigital.ai/
Beacon Harry Smith AI Data Centre Hub: https://beacondatacenters.com/campuses/
Beacon Indus Data Centre Hub: https://beacondatacenters.com/wp-content/uploads/2026/02/BEA_IndusCGY-FAQ.pdf
Beacon Heartland AI Data Centre Hub: https://beacondatacenters.com/campuses/
Beacon Saunders Lake AI Data Centre Hub: https://beacondatacenters.com/campuses/

## Slide 13
Alberta pipeline reference 2 of 3
Full identified core project and phase records.
Alberta Major Projects, 31 Aug 2026. ? = missing year; — = missing cost. Estimated scope varies.
13
Project / phase | Stage | Reported years | CAD B
Crusoe AI Data Centres Alberta | Proposed | ?–? | 3.00
HubOne AI & BTC High Density Compute Park | Proposed | ?–? | —
Prairie Sky Data Solutions Strathmore Data Center (Phase 1) | Proposed | ?–2026 | —
eStruxture CAL-1 Data Centre - Phase 4 Alterations | Construction | 2025–? | —
Blindman Industrial Park AI Data Centre | Construction | 2026–2026 | —
Technologies New Energy & Data District Data Centres (Phase 1) | Proposed | 2026–? | 1.26
Data Centre (Clive) | Proposed | 2026–? | —
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Names and reported values are preserved from the dated inventory. “Construction” abbreviates the publisher’s “Under Construction” status. Start and end years are reported years without back-calculation. These records are not a confirmed delivery forecast.
HubOne AI & BTC High Density Compute Park: https://hub1.ca/
Prairie Sky Data Solutions Strathmore Data Center (Phase 1): https://www.prairieskydata.com/

## Slide 14
Alberta pipeline reference 3 of 3
Full identified core project and phase records.
Alberta Major Projects, 31 Aug 2026. ? = missing year; — = missing cost. Estimated scope varies.
14
Project / phase | Stage | Reported years | CAD B
Mihta Askiy Data Centre | Proposed | 2027–? | —
Beacon Chestermere AI Data Centre Hub | Proposed | ?–2027 | —
K-Tech and Aurora AZ Energy Compute Facility | Construction | 2026–? | —
Meta Data Centre | Proposed | ?–? | 13.00
Malachite One Data Centre | Proposed | 2027–2030 | 15.00
Notes: Government of Alberta, Alberta Major Projects inventory, snapshot 31 August 2026. https://www.majorprojects.alberta.ca/
Methodology: https://majorprojects.alberta.ca/methodology
Names and reported values are preserved from the dated inventory. “Construction” abbreviates the publisher’s “Under Construction” status. Start and end years are reported years without back-calculation. These records are not a confirmed delivery forecast.
Beacon Chestermere AI Data Centre Hub: https://beacondatacenters.com/campuses/